## Projektstrukturplan
Projektstrukturplan
Update: | 22.02.2022
2022
| Tasks | Deadline | Status | January | February | March | April | May | June | July
Project management
| Goals (SMART) | 31.01.22
| Strategy (Project plan) | 31.01.22
| Requirements | 31.01.22
| Quality Management | 31.01.22
GitHub
Literature Review/Methodenkompetenz
| Collect Sources/Literature | 04.02.22
| Define Dataset | 04.02.22
| Write Review | 28.02.22
| Presentation | 28.02.22
Work Block 2
Establish Pipeline
Data Transformation
Comparison of ML models
Work Block 3
| Writing Master Thesis | 31.07.22
| Presentation/Defense Master Thesis | 31.07.22 | 20.01.: Date to be assigned
| Writing Paper | 31.07.22

## To-Do
To-Do
done
urgent
rejected
| Task | Deadline | Comment | Who?

## Pipeline_notes
Pipeline
Collection of Methods | comparison of machine learning methods with published packages (selbal, CODAcore. Etc.)
only filtering when over 1000 features
Steps | Methods | Comment
Pre-Processing | Filtering (e.g., 0.1% abundance, 10% samples, mRMR) | filtering should be implemented to reduce computational taxing; for zero-imputation, one extra next to zComposition as comparison
Zero-Imputation (zCompositions, mbImpute, Bayesian Imputation)
LASSO feature selection
univariate selection
Statistically Equivalent Signature algorithm
Transformation | CLR | by hand or selbal, easyCODA, or other packages; careful: for datasets correlating microbiomes with metabolites
ALR
ILR
Balances (selbal/discriminantive balance analysis, codacore)
Amalgamation (SLR)
Statistical Analysis | Mean, Median, Min., Max. | probably not part of the pipeline, until distributions are of interest
MAD
skweness
kurtosis
Kolmogorov-Smirnov test
Test/Training Split | 10-fold nested cross-validation | using empirical dataset to validate pipeline? Computation of bias L(Hold_out) - L(estimation)
stratification
30% partition for sub-sampling (n = 30)/70% for true performance estimation
small datasets: repeating inner CV loop to reduce variance
Models | Random Forrest (XGBoost) | recursive or normal SVM?
Logistic Regression
Support-Vector Machines
K-Nearest Neighbors
Neural Network
Linear Discriminant Analysis
PCA
Performance Metrics | Accuracy | Q: sensitivity analysis? See graph on the right as example for model performances for each data set
AUROC
PCC (Proportion of correct classifications)
RCI (entropy-based measures for uncertainty)
Statistical Indicators | random permutation testing to compare accuracies (see Statnikov)
McNemar's test
5x2-fold cross validation with modified paired students t-test
Wilcoxon signed rank test